## Phase 2 Timeline
VybeKart — Phase 2 Implementation Timeline
Prepared for: Hiren Prajapati ¦ Date: 20 May 2026 ¦ Target delivery: 01 June 2026
Scope: 7 core features + Payments & settlement recalculation + Amazon-format invoice generation. Live-stream UX / branding items from Phase2 spec are already completed (excluded from this plan).
IMPORTANT: Timeline is subject to change based on external factors (e.g. Razorpay merchant registration, Delhivery service registration). All other in-scope features not dependent on these third-party approvals will be completed within the stipulated timeframe below.
Executive Summary
Metric | Value | Notes
Core deliverables | 9 | 7 business features + Payments flow + Invoice generation
Development (parallel tracks) | 9 working days | 21 May 2026 – 29 May 2026
Integration testing & QA | 2 working days | 29 May 2026 – 01 June 2026
Total committed duration | 11 working days | Aligned to 1 June 2026 delivery
Target delivery / UAT-ready | 01 Jun 2026 | Staging build for client review
External dependencies | Razorpay, Delhivery | May shift payment/logistics go-live only; see note above
Excluded (already done) | Live UX + branding | Not part of this Phase 2 delivery plan
# | Feature / Module | Scope (from Phase2) | Platform | Est. Dev (days) | Est. QA (days) | Planned Start | Planned End | Dependencies / Notes
1 | Live stream seller rewards | Min 30 min/stream; 10 streams/30 days; dashboard status card; 0% commission on reward | Backend + Android Seller | 2 | 0.25 | 21-May-26 | 22-May-26 | Streams service, seller dashboard
2 | Replacement policy | 7-day window; replaceable up to 3 days; all eligible; customer replacement analytics | Backend + Android Buyer/Seller | 3 | 0.25 | 23-May-26 | 25-May-26 | Orders module
3 | Seller partner rating | Overall 0-5; Quality, Originality, Value sub-ratings; admin alert at 5; -2 penalty | Backend + Android | 2 | 0.25 | 26-May-26 | 27-May-26 | Replacement policy
4 | Followers & Following | Follow from live stream; profile: logo, store name, rating, replacement % | Backend + Android | 3 | 0.25 | 21-May-26 | 24-May-26 | Parallel with rewards / replacement
5 | Customer rating (internal) | Platform-only 0-5 from replacement ratio; email at 3 replacements; -2 penalty | Backend | 1 | 0.25 | 26-May-26 | 27-May-26 | Replacement analytics
6 | 24-hour cart expiry | Cart valid 24 hr after live stream; auto-clear after expiry | Backend + Android Buyer | 2 | 0.25 | 27-May-26 | 28-May-26 | Cart + stream end events
7 | Swipe up / down (live) | Gesture navigation during live streaming | Android | 1 | 0.25 | 28-May-26 | 28-May-26 | Live stream player
8 | Payments & settlement | MRP, logistics Rs.75, 2% gateway fee, 5% VybeKart commission, seller settlement per spec | Backend + Android Seller | 2 | 0.25 | 28-May-26 | 29-May-26 | Subject to Razorpay registration (external)
9 | Invoice (Amazon format) | PDF invoice with line items, fees, and settlement breakdown | Backend + PDF | 2 | 0.25 | 29-May-26 | 29-May-26 | Depends on payments module
- | Integration testing & UAT | E2E regression: live stream, cart, ratings, replacement, payments calc, invoice PDF | All platforms | - | 2 | 29-May-26 | 01-Jun-26 | In-scope features per rows 1-9 above
| Committed schedule (calendar) | Parallel development; delivery 01 June 2026 |  | 9 dev + 2 QA |  | 21-May-26 | 01-Jun-26
External factors (timeline may adjust for these only)
Factor | Impact on Phase 2 | In-scope features unaffected | Mitigation
Razorpay merchant registration | Live payment gateway activation / production keys | Rewards, replacement, ratings, followers, cart, swipe, settlement logic, invoice PDF |  |  |  | Implement & test on staging; go-live when registration completes
Delhivery service registration | Logistics API integration & live shipping rates | Same as above; logistics fee (Rs.75) logic can be built independently |  |  |  | Use configured logistics amount until API is active

## Milestones
Milestone | Date | Deliverable
Project kick-off | 21-May-2026 | Development start; staging environment ready
Sprint checkpoint | 25-May-2026 | Replacement + followers + rewards on staging
Feature development complete | 29-May-2026 | All 9 items code-complete on staging
QA / UAT complete | 01-Jun-2026 | Test sign-off; build shared for client review
Production release | 01-Jun-2026 | Go-live (payment/logistics live APIs per external approvals)
Note: Dates for production payment (Razorpay) and logistics (Delhivery) go-live may extend if third-party registration is pending. All other Phase 2 features remain committed to 01 June 2026.